## Slide 1
CONWIP - Constant Work In Progress
2017 by Thorbjørn Sigberg
https://www.miles.no/case-study-the-pursuit-of-flow-part-1/
https://www.miles.no/case-study-the-pursuit-of-flow-part-2/
https://kanbanize.com/blog/patrick-steyaert-customer-kanban/
The goal – to improve throughput and quality of the team efforts by limiting
the number of tasks on the Kanban board.
First improvement – set smaller WIP (Work In Progress) limits on columns.
The new board had up to 40 tasks in the following columns:
      Backlog (invisible) | Todo(10) | In progress(20) | Acceptance(10) | Done
We reduced 12 (!) different classes of service down to the following four:
Normal, Fixed deadline, Urgent, Critical
New tasks were selected based on priority, capacity and competence
Focus on unblocking and finishing existing tasks before starting new ones
Do not start new task without enough information/resources to complete it
Completed tasks are moved to “Acceptance”. It is not moved to “Done” until the customer accepted it.
“Stop starting and start finishing”
Better approach - limit the total number of tasks in the Kanban board instead of just limiting tasks per column.
CONWIP – use "tickets".
Each key account manager gets two "Todo tickets" to use on the Kanban board. Once placed on the board, the ticket would then be stuck to the task, until it had travelled all the way to the Done column. Only then would it be released back to the owner.
In addition, each of 7 account managers would get an extra (3rd) ticket for small, urgent tasks. So we had 14-21 tickets on the board. Also bugs/problems would not require a ticket, to ensure priority.
For faster rotation of tickets, account managers started to slice their tasks into smaller chunks. They were also more eager to help out with blocked tasks and helping to get customer's acceptance.
The effect was dramatic – more done in less time:
cycle time reduced from 10 to 4 days
lead time reduced from 4 weeks to 1 week
much less stress, less tasks in progress at any given time